| INTERNATIONAL PROJECT WORKSHOP 2023 – PROJECT ASSIGNMENT |  |  |
| --- | --- | --- |
| NAME OF THE COMPANY | TotalEnergies Marketing Česká republika s.r.o. |  |
| NAME OF THE PROJECT | PackBack! 2026 |  |
| PROJECT DESCRIPTION |  |  |
| Background & Challenge TotalEnergies Marketing Česká republika is committed to improving the sustainability and efficiency of its packaging return system. Although our contracts require customers to return packaging (pallets and IBCs) after use, this obligation has not been actively enforced. As a result, return rates remain below expectations—typically around 70–80%, while our internal target is 90% or higher. Starting January 1, 2026, our supply chain will be fully prepared to handle 100% of packaging returns. This creates a unique opportunity to redesign how we communicate and engage with customers regarding packaging returns. Project Mission Your mission is to help TotalEnergies rethink its packaging return management by delivering a fresh communication strategy, proposing next-generation customer communication tools, and applying bold marketing creativity. The goal is to support a behavioral shift among customers and strengthen the company’s sustainability efforts through innovative and customer-oriented approaches. What You’ll Work On The project consists of two interconnected layers: - External Communication Concept Propose a concept for a customer-facing communication tool. This could include ideas such as a webpage, anonymized rankings, return rate KPIs, or gamified elements (e.g., symbolic or real rewards within a defined budget). Technical implementation will be handled in-house, but your concept should be creative, feasible, and mindful of cybersecurity constraints. - Marketing Strategy Develop a formal, motivational, and educational marketing strategy to raise customer awareness and encourage better return behavior. Your strategy should support the company’s broader sustainability goals and be adaptable across different customer segments. Why It Matters This project is not just about communication—it’s about inspiring change. Through creativity and strategic thinking, you will help TotalEnergies build a more sustainable and efficient supply chain while fostering stronger customer relationships. |  |  |
| PROJECT SPECIFICATION |  |  |
| Goal | Deliver a comprehensive marketing strategy product consisting of two key components: an External Communication Concept and a Marketing Strategy. The final product will be developed in close cooperation with TotalEnergies stakeholders and delivered in two phases: - Creative Pitch Phase The project team will prepare and present a comprehensive pitch showcasing all possible solutions. TotalEnergies encourages maximum creativity—no idea is a bad idea. The most promising concept will be selected during the Mid-Term Review (see Milestones). - Strategy Development Phase The selected concept will be refined into a detailed strategy, including explanation of the approach, timeline, budget, and execution plan. This final version will be presented during the Project Showcase and should be ready for implementation. |  |
| Methods | The project will utilize the following methods: - Data storytelling to extract insights and communicate findings in a compelling way to customers - Conceptualization of IT solutions and front-end design to support usability, engagement, and clarity of communication - Development of a marketing strategy and communication plan to ensure alignment with TotalEnergies’ strategic direction and customer expectations |  |
| Tools | Microsoft Office, Graphics tools (Canva, Adobe Photoshop, etc.) |  |
| Inputs/Sources | The project will be based on the following internal data samples: - Current reporting of packaging return efficiency - Samples of Communication Guidelines (subject to verification by TotalEnergies) |  |
| Expected output | 1. External Concept Proposal - A conceptual design for a potential external communication tool - A solution proposal presented through a business case pitch 2. Marketing Strategy to Educate and Engage Customers - A marketing communication strategy tailored to support the change - Creative ideas to motivate and “win” customer interest and engagement |  |
| Acceptance criteria | The project will be evaluated based on the following qualitative criteria: - Overall coherence and sophistication - The final output demonstrates a high level of professionalism, clarity, and strategic alignment with the TotalEnergies goals. - Integration and synergy across both components - The two project layers—external concept and marketing strategy—are logically connected and reinforce each other as part of a unified solution. - Team’s ability to present, justify, and defend the project - The group can clearly articulate the rationale behind their approach, respond confidently to questions, and persuasively pitch their solution to stakeholders. |  |
| Project boundaries | Included in the Project Scope: - Creation of a concept and business case for a customer-facing communication tool - Design of a marketing strategy aimed at improving customer engagement and packaging return rates Excluded from the Project Scope: - Technical development or implementation of IT solutions intended for direct customer use |  |
| Milestones | We propose an agile project management approach supported by 2–3 structured review meetings: - Q&A Session #1: October 20–26 - Mid-Term Review: November 3–9 - Q&A Session #2: November 24–30 Key milestones will be defined through the stages of completion: 1. Q&A Session #1: October 20–26 – Concept Phase Review - Initial concepts and ideas drafted, following the “no idea is a bad idea” principle - Feasibility discussion held with TotalEnergies stakeholders 2. Mid-Term Review: November 3–9 – Product Pitch and Selection - Project team presents a pitch of the best available solutions to TotalEnergies stakeholders - Selection of the most promising concept by TotalEnergies 3. Q&A Session #2: November 24–30 – Review of selected strategy - Review of the selected concept and feedback on feasibility from TotalEnergies - Final adjustments before the Project Showcase |  |
| Other important information | N/A |  |
| REQUIREMENTS FOR PARTICIPANTS (What are the key abilities students should have in order they handle the project) |  |  |
| Must have | Good to have | Additional advantage |
| • Creativity and open-mindedness • Proficiency in Microsoft Office tools (Excel, PowerPoint, Word) | • Customer-focused mindset, including strategic thinking and positioning • Advanced Power BI skills for data visualization | • Experience with front-end website development or other front-end solutions related to external communication tools |
| NAME OF CONTACT PERSON IN THE COMPANY (TUTOR) | Václav Klusoň, Logistics and Supply Manager CE HUB vaclav.kluson@totalenergies.com, M. : +(420) 601 691 179 |  |
| OTHER USEFUL CONTACTS FOR MIAS | Eliška Kotek, Warehouse Supply Manager CE HUB, eliska.kotek@totalenergies.com Matěj Bakalář, Master Data Manager CE HUB, matej.bakalar@totalenergies.com |  |